## Acceptance Test Results
CS-97 Senior Capstone — Acceptance Test Results Tracker
Beantown Baby Diaper Bank ¦ Jungle Green Team: Dilanur Bayraktar, Cooper Golemme
# | Test ID | Description | Measured Result | Target / Tolerance | Status | Notes / Remediation Plan
Acceptance Criterion AC-1: Authorized administrators can upload diaper distribution data into the system
1 | 1A | Valid file upload and ingestion Upload test spreadsheet with 14 rows; verify all rows ingested, values match source, confirmation shown, data appears in distributions table. | 14/14 rows ingested. Values matched source file exactly. Confirmation message displayed. Data appeared in distributions table. | Row ingestion = 100% Numeric accuracy = exact match Processing ≤ 3 sec for 100 rows | PASS
2 | 1B | Invalid file rejection Upload ≥ 3 files with missing columns, invalid numerics, or malformed dates. | All 3 invalid files rejected with descriptive error messages. No partial data stored. | 100% invalid files produce error 0 invalid rows stored Error displayed ≤ 3 sec | PASS
3 | 1C | Latest data visible in application Upload valid spreadsheet; verify newly uploaded records appear in map and related views. | New records appeared in map view and admin table after upload. | Propagation to map ≤ 30 sec Data in admin view ≤ 3 sec | PASS
Acceptance Criterion AC-2: Uploaded data can be reviewed and edited by authorized administrators
4 | 2A | Field edit persists correctly Edit diaper count or org/city field for 10 existing records; verify persistence and visualization update. | All 10 edits saved successfully. Values persisted after page refresh. Visualization reflected updates. | Save success = 100% (10/10) Persistence = exact match Save response ≤ 3 sec per record | PASS
5 | 2B | Invalid edits are blocked Attempt negative counts, blank required fields, non-numeric values in numeric fields. | All invalid edit attempts were blocked. Validation messages displayed. No invalid records committed. | 100% invalid edits blocked 0 invalid records in DB | PASS
Acceptance Criterion AC-3: Data management features are protected by authentication and authorization
6 | 3A | Unauthenticated access is blocked Attempt to access upload, edit, and admin routes without logging in. | Redirected to login page on all protected route attempts. Admin UI elements not visible to unauthenticated users. | 100% of attempts blocked Redirect ≤ 2 sec | PASS
7 | 3B | General user access remains read-only Access as non-authenticated visitor; attempt data modification via interface and direct API requests. | Map, visualizations, and partner info accessible. Upload/edit features not accessible. All modification API requests rejected. | 100% modification attempts rejected 0 successful writes from general users | PASS
8 | 3C | Admin users can perform administrative data actions Log in as Admin; perform upload and edit workflows. | Admin successfully uploaded datasets and edited records. Changes saved and reflected in visualization. | 100% admin workflows succeed Updates visible ≤ 30 sec | PASS
9 | 3D | Only Super Admins can manage administrator accounts As Super Admin: create, reset, delete admin accounts. As Admin: attempt same actions. | Super Admin successfully created, reset, and deleted admin accounts. Admin user blocked from all account management features. | 100% Super Admin actions succeed 100% Admin account mgmt attempts blocked | PASS
Acceptance Criterion AC-4: Public users can explore diaper distribution data through an interactive map and timeline controls
10 | 4A | City exploration works correctly Click ≥ 10 cities with known seeded data; verify popup shows city name and correct yearly total. | Clicked 10 cities. All popups displayed city name and totals. Totals matched aggregated DB values in all cases. | 100% data accuracy vs DB totals Popup latency ≤ 1 sec | PASS
11 | 4B | Yearly data filtering works correctly Change selected year across multiple years including current incomplete year. | Year selector updated data correctly for all years tested. Current year displayed YTD totals. No monthly breakdown shown. | Aggregated totals = 100% accurate Visualization refresh ≤ 0.5 sec | PASS
12 | 4C | Basic usability and performance Load on desktop (1440px, 768px) and mobile (375px) viewport sizes. | Map remained interactive and readable at all three viewport widths. No layout failures or UI errors. City/partner interactions functional. | Page load ≤ 5 sec No layout failures at 375/768/1440 px | PASS
Acceptance Criterion AC-5: Users can explore partner organization information connected to the distribution data
13 | 5A | Partner organizations appear for a selected area Click locations with known partner associations in seeded test data. | Correct partner icons/names displayed for all tested locations. Partner association matched expected seeded data. | Partner association = 100% accurate | PASS
14 | 5B | Partner detail popup is complete and correct Click ≥ 10 partner icons; verify popup shows all required fields. | All 10 partner popups showed: org name, description, partnership start date, and approx babies helped/month. All values matched stored records. | 100% field completeness Data = exact match to stored records Popup display ≤ 1 sec | PASS
Summary
| Total Tests | 14
| Passed | 14
| Failed | 0
| Pending | 0
| Overall Status | ALL CRITERIA MET